## Sprint 1
Functional Testing Case Study - 1
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://www.maxfashion.in/
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the Dependacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Max Fashion is a leading Indian fashion retail brand offering affordable clothing, accessories, and footwear for men, women, and children. It operates both physical retail stores and an e-commerce platform through its official website https://www.maxfashion.in/in/en. The platform allows users to browse various product categories, apply filters, manage user accounts, shop online, and make payments securely. Max Fashion provides an intuitive and user-friendly interface, helping customers to search and purchase products seamlessly. It also offers personalized deals, sign-in via mobile OTP, wishlist/favorites, and checkout options for both guest and registered users. FUNCTIONALITY IN THE SCOPE (What Functionalities to TEST): 1) Signing In On opening the Max Fashion website, the user can click Sign In to log in using a registered mobile number. A secure OTP is sent to the user’s mobile, which must be entered for verification. After successful login, the user is redirected to the homepage. Sign-in is essential for accessing order history, favorites, and profile management. 2) Browsing Categories The homepage has navigation options for Men, Women, and Kids categories. On hovering over each category, sub-categories like T-Shirts, Jeans, Dresses, and Footwear appear. The user can click on any category to open the respective product listing page. Filters such as Size, Brand, Price, Color, and Age can be applied to narrow down search results. 3) Product Filters and Sorting Product listing pages allow sorting by Price, Popularity, or Newest. Users can apply multiple filters such as brand (e.g., MAX), price range, and size (e.g., M, L, XL). Filtered results are dynamically updated without full page reload. 4) Favorites / Wishlist Users can click on the Heart icon to add any product to the favorites list. The favorites list can be accessed later for quick product review or addition to cart. Only signed-in users can manage and view their wishlist. 5) Add to Cart & Remove from Cart After selecting size, a product can be added to cart using the Add to Cart button. The cart icon on the top right updates the number of items dynamically. Users can remove items from the cart and verify if cart count decreases accordingly. 6) Checkout and Payment Checkout involves entering shipping details, selecting delivery options, and choosing a payment method (Card, UPI, COD). For signed-in users, saved addresses are auto-filled. Payment gateway redirection and confirmation message validations are included. An order summary page confirms purchase with estimated delivery time. 7) Kids & Women Categories Similar to men’s section, users can explore the Women’s and Kids’ collections. Options to apply age filters (e.g., 2-4 yrs, 6-8 yrs) for Kids category. Gender-specific and size-specific filters for women’s wear. 8) Customer Support / Help Section A Help/FAQ link is available in the footer. Customers can access information about order tracking, returns, shipping policies, and size guides. There's a Contact Us option for email or chat support. Expected Implementations: Test Design Techniques: Equivalence Partitioning (EP) Boundary Value Analysis (BVA) Decision Table Testing Use Case Testing Error Guessing Types of Testing: Functional Testing Integration Testing System Testing Regression Testing UI Testing Smoke and Sanity Testing Expected Additional Testing (Optional but Recommended): Load Testing: To assess performance under user load during sales or peak hours. Localization Testing: Ensure correct regional formats (₹ currency, pin codes). Volume Testing: Product listing, cart load, and multiple filters applied together. Test Data: Valid and invalid mobile numbers for login OTP combinations (valid, expired, wrong) Filter values (e.g., sizes, price ranges) Products with limited stock for add/remove cart validation
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report Keep all the Deliverables on Git
Sprint Day 5 | Sprint Evaluation

## User Stories
Issue Type | Summary
Epic 1 | Sign in
Story 1 | As a registered user, I want to sign in using my mobile number, so that I can access my account securely.
Story 2 | As a registered user, I want to enter the valid OTP for logging in, so that I can authenticate my identity.
Story 3 | As a user, I want to receive an error message for invalid OTP or incorrect mobile number, so that I can correct my input and retry.
Epic 2 | Men's Products
Story 1 | As a male customer, I want to hover over the Men's category on the homepage, so that I can explore the available product categories like T-Shirts, Shirts, Jeans, etc.
Story 2 | As a user, I want to click on T-Shirts under the Topwear section of the Men’s category, so that I can navigate directly to the relevant product listings.
Story 3 | As a user, I want to apply filters on the left side such as Sizes (L, M, XL), so that I only view the products that match my size preferences.
Story 4 | As a user, I want to set the price filter to a minimum of ₹500 and maximum of ₹1000, so that I can browse only affordable T-shirts within my budget.
Story 5 | As a user, I want to add the filtered product to Favorites, and later move it to the cart after selecting the required size, so that I can buy it easily.
Story 6 | As a user, I want to have the option to remove the product from the cart after adding it, so that I can manage and review my purchase decision before final checkout.
Epic 3 | Women's Products
Story 1 | As a female customer, I want to hover on the Women category on the homepage, so that I can see subcategories like Tops, Kurtas, Dresses, etc. and navigate easily.
Story 2 | As a user, I want to click on Tops or any subcategory and be taken to a listing page where I can view products specific to that category.
Story 3 | As a user, I want to apply brand and size filters such as "S, M, L" and favorite brands, so that I can narrow down my options based on preferences.
Story 4 | As a user, I want to set a price filter such as ₹600–₹1200, so that I can browse products within a budget without going through expensive items.
Story 5 | As a user, I want to add items to favorites, and then select a size and move them to the basket, so that I can check out easily when ready.
Story 6 | As a user, I want to have the option to remove a product from the basket, in case I change my mind about purchasing it.
Epic 5 | Kids Products
Story 1 | As a customer, I want to hover over the Kids section on the homepage to view all available categories like Boys, Girls, Infants, etc., so that I can explore appropriate product options.
Story 2 | As a user, I want to click on Shirts or Topwear for Kids to see clothing options tailored for different age groups, so that I can easily shop for children.
Story 3 | As a user, I want to filter Kids clothing based on size (4–5Y, 6–7Y, etc.), so that I only see clothes that fit the child I’m shopping for.
Story 4 | As a user, I want to set a price range filter, for example from ₹300 to ₹800, so that I can stick to a specific budget while shopping.
Story 5 | As a user, I want to add selected items to favorites, and then move them to the cart after reviewing, so that I can make quicker decisions later.
Story 6 | As a user, I want the ability to remove any item from the cart, so that I can change my selection before placing the order.
Epic 5 | Chec Out & Payment
Story 1 | As a user, I want to review all the products in my cart along with their quantities, sizes, and prices, so that I can confirm everything before proceeding to checkout.
Story 2 | As a customer, I want to remove or update product quantity directly from the cart page, so that I have complete control over what I’m purchasing.
Story 3 | As a user, I want to proceed to checkout from the cart and be asked to fill or verify my delivery address, so that I ensure accurate delivery details.
Story 4 | As a user, I want to choose from multiple payment methods like UPI, Credit/Debit Card, Net Banking, or COD, so that I can use the option that suits me best.
Story 5 | As a user, I want to apply coupons or promo codes during payment, so that I can avail of discounts or offers available.

## Test Scenario
TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
TCL_001 | Epic1_Story1 | Verify successful login with mobile number | Functional Testing | 2 | 1. Enter valid Phone number 2. Click on submit 3. Enter OTP 4.User redirected to home page
TCL_002 | Epic1_Story2 | Validate error message for invalid mobile number | Negative Testing | 2 | 1. Enter invalid mobile number 2. Click Sign in 3. System shows "Invalid mobiler number" message
TCL_003 | Epic1_Story3 | Verify OTP entry and authentication process | Functional Testing | 3 | Valid OTP, expired OTP, incorrect OTP, empty OTP
TCR_001 | Epic2_Story1 | Verify hovering over Men’s category displays subcategories | UI/Functional Testing | 2 | Hover over Men’s tab, check listed subcategories
TCR_002 | Epic2_Story2 | Verify clicking on T-Shirts navigates to correct product listing | Functional Testing | 1 | Click navigation, verify T-shirt listing
TCR_003 | Epic2_Story3 | Verify filters apply for sizes (L, M, XL) | Functional Testing | 1 | Apply size filters, validate filtered results
TCR_004 | Epic2_Story4 | Verify price filter from ₹500 to ₹1000 functions correctly | Functional Testing | 2 | Apply min, max, and both filters
TCR_005 | Epic2_Story5 | Verify adding filtered item to favorites and moving to cart | Functional Testing | 2 | Add to favorites, view favorites, move to cart, verify item in cart
TCR_006 | Epic2_Story6 | Verify option to remove product from cart | Functional Testing | 2 | Remove item, confirm it's removed from cart
TSB_001 | Epic3_Story1 | Verify hovering over Women’s category displays subcategories | UI/Functional Testing | 3 | Hover on Women’s tab, check categories
TSB_002 | Epic3_Story2 | Verify click on Tops navigates to correct listing | Functional Testing | 2 | Click navigation, validate listing
TSB_003 | Epic3_Story3 | Verify filters for size and favorite brand work correctly | Functional Testing | 1 | Apply size, brand, and combination filters
TSB_004 | Epic3_Story4 | Verify price filter between ₹600–₹1200 works | Functional Testing | 2 | Apply price filters separately and together
TSB_005 | Epic3_Story5 | Verify user can add to favorites and then move to cart | Functional Testing | 1 | Add to favorites, view list, move to cart, confirm item in cart
TSB_006 | Epic3_Story6 | Verify user can remove item from cart | Functional Testing |  | Remove product, validate removal
TCS_001 | Epic4_Story1 | Verify Kids section shows Boys, Girls, Infants | Functional Testing | 3 | Hover on Kids, validate all categories
TCS_002 | Epic4_Story2 | Verify clicking on Shirts or Topwear shows correct products | Functional Testing | 2 | Click navigation, check listing accuracy
TCS_003 | Epic4_Story3 | Verify filtering by age group (4-5Y, 6-7Y) works | Functional Testing | 1 | Apply age filter, validate displayed results
TCS_004 | Epic4_Story4 | Verify price filter (₹300–₹800) works | Functional Testing | 2 | Apply price ranges and check filtered items
TCS_005 | Epic4_Story5 | Verify selecting item to favorites and moving to cart works | Functional Testing | 2 | Add to favorites, view, move to cart, confirm item in cart
TCS_006 | Epic4_Story6 | Verify removing item from cart | Functional Testing | 1 | Remove product, check cart update
TCD_001 | Epic5_Story1 | Verify reviewing all items in cart with details | Functional Testing | 1 | View cart items, verify prices and sizes
TCD_002 | Epic5_Story2 | Verify ability to remove or update quantity in cart | Functional Testing | 1 | Update quantity, remove item, validate result
TCD_003 | Epic5_Story3 | Verify checkout process and delivery address confirmation | Functional Testing | 1 | Proceed to checkout, enter/edit address, verify
TCD_004 | Epic5_Story4 | Verify multiple payment options work correctly | Functional Testing | 1 | Select UPI, Card, NetBanking, COD – test all options
TCD_005 | Epic5_Story5 | Verify coupons or promo codes are applied correctly | Functional Testing | 1 | Apply valid coupon, invalid coupon, expired code

## Test Case Template
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 (to be updated only if test case failed in Iteration 1) | Status Iteration 2 (to be updated only if test case failed in Iteration 1) | Comments | Req: Reference
TCL_001 | Sign in with valid mobile number | User is on the sign-in page | Valid mobile number entered | 1. Open the browser and go to https://www.maxfashion.in/in/en 2. On the homepage, locate and click the “Sign In” button present at the top-right corner of the screen 3. In the mobile number field, enter a valid registered number 4. Click on the “Send OTP” button to receive the one-time password 5. Enter the correct OTP received via SMS 6. Click on the “Submit” button to log in | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | User is signed in successfully and redirected to the homepage
TCL_002 | Sign in with invalid OTP | User is on OTP screen | Invalid OTP | 1. Open the Max Fashion website: https://www.maxfashion.in/in/en 2. Click on the “Sign In” option 3. Enter a valid mobile number and click “Send OTP” 4. When the OTP input appears, type an incorrect OTP 5. Click on the “Submit” button to attempt login | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | Error message displayed: “Invalid OTP. Please try again.”
TCL_003 | Sign in with already logged-in user | User is already logged in from previous session | Clicking the Sign In option when logged in | 1. Ensure user is signed in from previous session (cookies active) 2. Visit: https://www.maxfashion.in/in/en 3. Click Sign In or profile icon again 4. System checks session and redirects to user account/dashboard without asking OTP | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | User is redirected to their profile/account
TCR_001 | Browse Men's Categories | User is on homepage | Hover over "Men" section | 1. Open browser and go to: https://www.maxfashion.in/in/en2. Wait for homepage to load completely 3. Hover the mouse over the Men tab in the top navigation bar 4. Observe the dropdown showing subcategories such as T-shirts, Shirts, Jeans, Trousers, etc. | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | All Men's subcategories should appear as a dropdown
TCR_002 | Filter Men's T-shirts by Size | On Men’s listing page | Size filter interaction | 1. Visit https://www.maxfashion.in/in/en 2. Hover over Men and click on T-Shirts from the dropdown 3. On the product listing page, locate the Size filter panel 4. Select sizes L and XL 5. Wait for the page to reload with applied filters | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 Sizes:L,XL | Only matching size products displayed
TCR_003 | Apply Price Filter | On Jeans listing page | Price filter selection | 1. Navigate to https://www.maxfashion.in/in/en 2. Hover over Men > Click on Jeans 3. On the left-hand filter sidebar, locate the Price section 4. Select the price range ₹500–₹1000 5. Wait for page to reload with updated product results | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | Only jeans within the selected price range are shown
TCR_004 | Add to Favorites and Cart | User is signed in | Use of Heart & Cart icons | 1. Log into the Max Fashion website using a valid mobile number and OTP 2. Go to any Men’s product page (e.g., Men > T-Shirts) 3. Click on the heart icon to add product to Favorites 4. Navigate to Favorites section from user profile 5. Click on Add to Cart | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | Product is successfully moved from Favorites to Cart
TCR_005 | Remove product from the cart | User is signed in and cart has product | Remove item from the cart | 1. Open the browser and go to https://www.maxfashion.in/in/en 2. Sign in using a valid mobile number and OTP 3. Navigate to Men > T-Shirts and select any product 4. Click Add to Cart 5. Click on the Cart icon on the top right corner 6. In the Cart page, locate the added product 7. Click on the Remove or Delete icon beside the product 8. Confirm the action if prompted | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | Product is removed from the cart successfully
TCB_001 | Browse Women’s Categories | User is on homepage | Navigate to Tops category | 1. Open a web browser (e.g., Chrome) 2. Navigate to the URL: https://www.maxfashion.in/in/en 3. Wait for the homepage to load completely 4. Locate the top navigation bar 5. Hover over the Women section 6. In the dropdown, click on Tops | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | User is redirected to the Women Tops product listing page
TCB_002 | Filter Women Tops by Brand and Size | User is on Women Tops page | Apply Brand and Size filters | 1. On the Women > Tops product listing page 2. Locate the left-hand filters panel 3. Under Brand, select checkbox for MAX 4. Under Size, select checkbox for M 5. Wait for products to reload based on selected filters | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | Product list displays only MAX brand tops in size M
TCB_003 | Filter by Price Range | User on listing page | Select price range filter | 1. After applying brand and size filters (optional), locate the Price filter on the left panel 2. Use the slider or enter the range manually to select ₹600 as the minimum and ₹1200 as the maximum 3. Click Apply or wait for auto-refresh | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | Only products within the selected price range are displayed
TCB_004 | Add to Cart from Favorites | User is on Favorites page | Add item from Favorites | 1. Ensure user is signed in and has already added a product to Favorites 2. Navigate to https://www.maxfashion.in/in/en 3. Click on the Heart/Favorites icon at the top-right corner 4. On the Favorites page, locate a product 5. Click Add to Cart | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | Product is removed from Favorites and added to Cart
TCB_005 | Remove one item from cart | Product is added to cart | Click remove icon/button | 1. Navigate to https://www.maxfashion.in/in/en 2. Add a product to the cart 3. Click the cart icon in top-right 4. Locate the added product 5. Click on trash icon or Remove button beside the product | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | The selected product is removed, and the cart is updated
TCS_001 | Navigate to Boys' Clothing | User is on homepage | Hover to Kids > Boys Clothing | 1. Open a web browser and go to https://www.maxfashion.in/in/en 2. Allow the homepage to load fully 3. Locate the top navigation menu 4. Hover the mouse over Kids category 5. From the dropdown menu, click on Boys Clothing 6. Wait for products to load | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | The Boys' Clothing product listing page is displayed successfully with relevant products shown
TCS_002 | Add Kidswear to Cart | User is logged in or guest | Product selected and added to cart | 1. Navigate to the desired kidswear product from Kids > Boys Clothing 2. Click on the product to view details 3. Select a suitable size (e.g., S, M, L) 4. Click on Add to Cart button 5. Click on Cart icon in top-right corner to verify cart contents | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | Product is added to the shopping cart, and the cart icon updates to show correct item count
TCS_003 | Apply Age Filter | On Kids category listing | Filter products by Age group | 1. Navigate to the Kids category page or any kidswear listing 2. Wait for all filters to load on the left sidebar 3. Scroll to the Age filter section 4. Select the checkbox for 4–6 Years 5. Wait for the page to refresh with filtered results | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | Only the products appropriate for 4–6 years age group are shown in the listing
TCS_04 | Remove item during checkout page | Product in cart, checkout | Remove item on checkout | 1. Add any product to cart 2. Go to cart and click Proceed to Checkout 3. On checkout page, view list of items 4. Click Remove beside the item 5. Observe the price update and item removal from checkout summary | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | Product is removed instantly, order total recalculated
TC_01 | Proceed to checkout with 1 item | Product added to cart | Begin checkout | 1. Open browser and go to https://www.maxfashion.in/in/en 2. Sign in or proceed as guest 3. Add any product to the cart 4. Click on the cart icon (top right) 5. Click on Proceed to Checkout button 6. Verify navigation to checkout page | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | User is taken to the checkout page where shipping details can be entered
TC_02 | Enter shipping and contact details | On checkout page | Fill delivery information | 1. On the checkout page 2. Enter valid Name, Mobile Number, Pincode, Address, City, and State 3. Select delivery method if available 4. Click Continue to Payment | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | Shipping details accepted and user moves to payment options
TC_03 | Make payment using UPI | On payment screen | Select UPI | 1. On Payment Page 2. Select UPI as payment method 3. Enter valid UPI ID (e.g., user@okaxis) 4. Click Pay Now 5. Approve payment on UPI app 6. Wait for success confirmation | https://www.maxfashion.in/ Mobile number:8125801595 OTP:00000 | Payment is processed, order placed, and success screen shown
TCG_003

## Defect Report
Defect Id. | Module name | Defect Summary | Defect Priority | Assigned To | Status

## Sprint 2
Automation Testing Case Study - 1
Following website is given for Automating Testing using Selenium Automation Page Factory/POM, TestNG & BDD Framework (using Cucumber)
Url: http://phptravels.net/
Sprint Day # | Task / Scenario Given | Deliverables at the EoS Day#
Sprint Day 1 | 1. Identify the Manual Test Cases that you want to automate. | 1. Creation of Project Structure
| 2. Plan the flow of application that you want to test using automation test scripts. | 2. Creation of Feature File.
3. Create a Maven Project - Associate required libraries with the Maven Project
4. Configure required dependencies like Selenium WebDriver, TestNG / Junit, Cucumber etc. in POM.xml
5. Creation of Feature File
Sprint Day 2 | 1. Create the required Feature files with relevant scenarios (User Stories) using Gherkin continue. | 1. List of Feature Files :
| · Use Scenario Outline & Examples to implement Parametrization in Feature File | 2. List of Test Cases :
| 2. Implement Page Factory or Object Repository (XML/Property File) to identify and store all the web elements. | 3. Prioritization of tests :
| · Use all types of Locators | 4. Test Runner class Parameters
| · Ensure appropriate usage of Selenium Web Driver API objects and import statements | 5. Report File Names
3. Design the test runner class
Sprint Day 3 | 1. Implement parametrization using apache POI
| 2. Implement TestNG for generating reports and XML file for parallel execution of test suite | 1. Parametrization Sample Data :
| 3. Generate Step Definitions and write the Tests addressing all the functional requirements. | 2. Report File Names
3. Generating Step Defination File
Sprint Day 4 | 1. Generate Step Definitions and write the Tests addressing all the functional requirements | 1. Detail Test Script in Step Definitions
| · Implement Assertions/Verifications using TestNG | 2. Feature File- Test Case – PF/OR collation in an Excel sheet
· Use appropriate wait statements
· Handle new windows, popup’s, navigations
2. Ensure implementation of good programing practices
· Variable, Function & procedure naming convention
· Usage of comments
· Code Indentation
Sprint Day 5 | 1. Generate Step Definitions and write the Tests addressing all the functional requirements Continue | 1. Detail Test Script in Step Definitions
2. Feature File- Test Case – PF/OR collation in an Excel sheet
Sprint Day 6
| 2. Finally generate TestNG/XML Test report mentioning pass/fail status. | 1. Test Reports
Sprint Day 7 | 1. Jenkins Implimentation 2. Project Closure | 1. Create build using Jenkins
Sprint Day 8 | Sprint Evaluation